## 20150610
Enet I
| No. | Category | Task(Use case) | Status | person responsible | deadline | Comment | Reviewer | Result
| 1 | MVC | Master page with menu | in progress | Jiabao | 2015-06-13
| 2 | MVC | Homepage | in progress | Jiabao | 2015-06-13 | like iss homepage
| 3 | MVC | Course List with category sidebar | in progress | Jiabao | 2015-06-13 | adjust sidebar, hide disabled course
| 4 | MVC | Course detail with upcoming class | in progress | Jiabao | 2015-06-13
| 5 | MVC | Course search | in progress | Jiabao | 2015-06-13 | almost done, adjust present fields
| 6 | MVC | Course registration for public | in progress | Jiabao | 2015-06-13
| 7 | MVC | Course registration for IndividualUser | in progress | Jiabao | 2015-06-13
| 8 | MVC | Course registration for CompanyHR | in progress | Jiabao | 2015-06-13
| 9 | MVC | User registration | Done | Charan | 2015-06-13 | after registration, should forward to right page
| 10 | MVC | User Login | Done | Charan | 2015-06-13 | if default password, need prompt to change password after, staff user should forward to webform pages
| 11 | MVC | Change/reset password | Done | Charan | 2015-06-13
| 12 | MVC | CompanyInfo | in progress | Charan | 2015-06-13 | Company Info with HR info
| 13 | MVC | CompanyEmployee list | Done | Minsheng | 2015-06-13
| 14 | MVC | CompanyEmployee's registration list | Done | Liu | 2015-06-13 | almost done, adjust present fields
| 15 | WebForm | Master page for CourseAdmin | in progress | Liu | 2015-06-13
| 16 | WebForm | Course List | Done | Minsheng | 2015-06-13
| 17 | WebForm | Course Detail | Done | Minsheng | 2015-06-13 | bonus point, show class list
| 18 | WebForm | Class List | Done | Liu | 2015-06-13 | almost done, adjust present fields' order add a button [print attendsheet]
| 19 | WebForm | Class Detail | Done | Liu | 2015-06-13 | bonus point
| 20 | WebForm | Registration List | Done | Minsheng | 2015-06-13
| 21 | WebForm | Registration Detail | Done | Minsheng | 2015-06-13
| 22 | WebForm | Master page for SystemAdmin | Done | Liu | 2015-06-13
| 23 | WebForm | User Management | Done | Charan | 2015-06-13
| 24 | WebForm | Print attendance sheet | in progress | Avishek | 2015-06-13
| 25 | Overall | Authentication & Authorization implement | in progress | Minsheng | 2015-06-13
| 26 | Overall | SiteMap | Done | Liu | 2015-06-13
| 27 | Overall | System Architecture & infrastructure | Done | Minsheng | 2015-06-13
| 28 | Overall | Email Sending | Done | Charan | 2015-06-13
| 29 | Overall | Domain Model | Done | Minsheng | 2015-06-13
30
Enet II
| No. | Category | Task(Use case) | Status | person responsible | deadline | Comment | Reviewer | Result
| 34 | WCF | Course Registration Service | Done | Minsheng | 2015-06-13
| 35 | WCF | Submit Attendance Service | Done | Minsheng | 2015-06-13
| 36 | WCF | Host Application | in progress | Avishek | 2015-06-13 | with binding option and justifications
| 37 | WCF | WCF Security | in progress | Avishek | 2015-06-13
| 38 | WWF | Course Confirmation Process | in progress | Liu, Jiabao | 2015-06-13
| 39 | WWF | Course Completion Process | in progress | Charan | 2015-06-13
| 40 | Client Application | Client Application | in progress | Avishek | 2015-06-13 | for testing above service
| 41 | WebForm | Class management trigger WWF | in progress | Liu | 2015-06-13
System Testing & Presentation preparation